Committee on Contracts Staff:

Alex R. Paulenoff, Senior Legislative Counsel

Johari Frasier, Legislative Counsel

Alex Yablon, Policy Analyst

Owen Kotowski, Financial Analyst

Committee on Transportation and Infrastructure Staff:

Sierra Townsend, Legislative Counsel

Theodore Miller, Legislative Analyst

Kevin Kotowski, Senior Policy Analyst

John Basile, Senior Policy Analyst

Adrian Drepaul, Principal Financial Analyst

Committee on Cultural Affairs, Libraries and International Relations Staff:

Alejandro Carvajal, Legislative Counsel

Regina Paul, Senior Policy Analyst

Carolina Gil, Financial Analyst

#### THE COUNCIL OF THE CITY OF NEW YORK

COMMITTEE REPORT OF THE LEGISLATIVE DIVISION

Andrea Vazquez, Director

Rachel Cordero, Deputy Director, Governmental Affairs Division

Bradley J. Reid, Deputy Director, Infrastructure Division

Smita Deshmukh, Deputy Director, Human and Social Services Division

##### COMMITTEE ON CONTRACTS

#### Hon. Lincoln Restler, Chair

##### COMMITTEE ON TRANSPORTATION AND INFRASTRUCTURE

#### Hon. Shaun Abreu, Chair

##### COMMITTEE ON CULTURAL AFFAIRS, LIBRARIES AND INTERNATIONAL RELATIONS

#### Hon. Dr. Nantasha Williams, Chair

April 29, 2026

Oversight – Capital Construction Contracting and Cost Escalation

INT. NO. 263:	By Council Members Krishnan, Louis, Brooks-Powers, Abreu, Brewer, Hudson, Hanif, Stevens, Ung, Feliz, Schulman, Gutiérrez and Morano

TITLE:	A Local Law in relation to developing a strategic blueprint to reduce capital project durations by at least 25 percent

INT. NO. 465:	By Council Members Stevens, De La Rosa, Farías, Brooks-Powers, Williams, Louis, J. Sanchez, Schulman, Riley, Dinowitz and P. Sanchez

TITLE:	A Local Law in relation to a study and report on the expansion of ferry service along the Harlem River

RES. NO. 264:	By Council Members Lee, Louis, Feliz and Schulman

TITLE:	Resolution calling on the New York State Legislature to introduce and pass, and the New York State Governor to sign, legislation to grant permanent and expanded Design-Build authority to all New York City agencies

INTRODUCTION

On April 29, 2026, the Committee on Contracts, chaired by Council Member Lincoln Restler; the Committee on Transportation and Infrastructure, chaired by Majority Leader Shaun Abreu; and the Committee on Cultural Affairs, Libraries and International Relations, chaired by Deputy Speaker Dr. Nantasha Williams; will conduct an oversight hearing entitled “Capital Construction Contracting and Cost Escalation.” In addition, the Committees will hear the following legislation: Introduction Number (“Int. No.”) 263, sponsored by Council Member Krishnan, in relation to developing a strategic blueprint to reduce capital project durations by at least 25 percent; Int. No. 465, sponsored by Council Member Althea Stevens, in relation to a study and report on the expansion of ferry service along the Harlem River; and Res. No. 264, sponsored by Council Member Lee, calling on the New York State Legislature to introduce and pass, and the New York State Governor to sign, legislation to grant permanent and expanded Design-Build authority to all New York City agencies. Those invited to testify include representatives from the New York City (“NYC” or “the City”) Department of Design and Construction (“DDC”), NYC Mayor’s Office of Contract Services (“MOCS”), NYC Department of Transportation (“DOT”), NYC Department of Cultural Affairs (“DCLA”), construction firms, think-tanks, advocates, and others.

BACKGROUND

Agencies

Department of Design and Construction

DDC is the City’s primary capital construction manager and builds many of the City’s civic facilities, including firehouses, libraries and police precincts. DDC also designs and improves vital infrastructure throughout the City, delivering roadway, sewer and water main construction projects in all five boroughs. DDC collaborates with more than 20 City agencies on infrastructure and public building projects, and works with nonprofits that receive funding from the City.

Mayor’s Office of Contract Services

MOCS is an oversight and service agency that works with other agencies on procurement of goods and services from outside vendors. MOCS establishes policies, procedures and guidelines for the implementation of Procurement Policy Board rules and local laws. MOCS is authorized to perform pre- and post-audit reviews and to provide all necessary determinations, approvals, and certifications related to agency procurement actions. MOCS is also responsible for maintaining the City’s central contract registry. The office administers the Procurement and Sourcing Solutions Portal (“PASSPort”), a digital platform that tracks every stage of the procurement process.

Department of Transportation

DOT’s self-described mission is to provide for the safe, equitable, and sustainable movement of people and goods in NYC, while creating public spaces that strengthen the City’s communities. The agency’s vision is a transportation system that provides equitable mobility for all residents and visitors, while also being environmentally sustainable and built to adapt to the threat of climate change. DOT is responsible for a significant amount of the City’s public infrastructure, which includes planning, design, construction, maintenance, and management of roads, sidewalks, bridges, traffic signals and signs. DOT has an annual operating budget of $1.5 billion and a 10-year $33.5 billion capital program, with nearly 6,000 employees. Overall, DOT manages 6,300 miles of streets and highways, over 12,000 miles of sidewalk, approximately 800 bridges and tunnels, over one million street signs, 13,500 signalized intersections, nearly 400,000 streetlights, over 350 million linear feet of markings, 15,000 parking meters and 37 parking facilities, and the Staten Island Ferry.

Department of Cultural Affairs

DCLA is the municipal agency dedicated to supporting and strengthening the City’s cultural sector to ensure that the arts remain a vital part of the City’s civic and economic life. A core part of DCLA’s mandate is to administer and distribute public funding for non-profit cultural organizations throughout the five boroughs. The agency partially funds the energy and operations costs of the 39 entities in the Cultural Institutions Group (“CIGs”) which are privately managed organizations operating in public facilities. DCLA also administers the Cultural Development Fund (“CDF”), which distributes grants through a peer-review process to cultural organizations. DCLA also provides capital funding for design, construction, and equipment for cultural facilities in both City-owned and non-City-owned spaces. DCLA is primarily structured into three funding divisions corresponding with these functions: a unit that administers the CDF, a unit that provides operational support to the CIGs, and a unit that provides capital design, construction and equipment funds for CIG and non-CIG cultural groups. DCLA’s budget for Fiscal Year 2026 was $299.6 million at adoption.

Rising Capital Construction Costs

Construction costs in the City are the highest in the world, with an average project cost of $534 per square foot. In fact, construction projects in the City have an average project cost seven percent greater than San Francisco, the next most expensive city in the world to build. NYC’s high cost per square foot arises from expensive labor, the rising cost of materials, the “soft costs” of pre-construction planning and permitting, and high land values.

Labor

Overall, labor costs add significantly to the cost of capital projects in NYC. While the average construction wage nationally is $76 per hour, City construction workers make an average hourly wage of $131.40. Local regulations can further increase labor costs for certain specializations, while lowering the overall eligible workforce. For example, crane operators must meet stringent licensing requirements to operate in the City. In addition, insurance and workers’ compensation costs are high because of New York State Labor Law Section 240, also known as the “Scaffold law,” which courts have interpreted to impose absolute liability on contractors for workplace injuries that occur at height, meaning the companies must pay even in cases where they took required safety precautions or the injured party was negligent.

Furthermore, New York State (“NYS”) Labor Law Section 220 requires all workers employed on publicly funded projects to receive prevailing wages and benefits, which are typically close to union rates, since they are set in Collective Bargaining Agreements between unions and the City and are thus higher than wages for non-union construction jobs. Prevailing wage laws are written with the intent of reducing overall downward pressure on wages, which is to say, they are designed to keep labor costs elevated. Policy experts contest the impact of prevailing wage requirements on overall project costs. For example, conservative groups have projected prevailing wage requirements increase overall project costs by 13 to 25 percent depending on region, while pro-labor voices argue that the impact on total cost is minimal since higher wages reduce turnover and attract more productive workers, offsetting the costs of those higher wages and benefits. In 2016, the City’s Independent Budget Office estimated prevailing wage laws increased total construction costs by 23 percent.

On a national level, labor costs have increased due to the Trump Administration’s aggressive crackdown on immigration. According to a 2025 Pew Research Center report, construction has the highest share of undocumented immigrant employees of any industry, an estimated 15 percent of all workers. Construction firms report fears of arrest and deportation have made labor scarce, causing delays and incurring higher costs for all projects regardless of whether firms had hired undocumented workers or not.

Materials

Construction material prices surged for a variety of reasons since the onset of the COVID-19 pandemic in early 2020. Initially, the pandemic and associated lockdown measures throughout the world severely disrupted international supply chains for inputs ranging from raw materials like lumber and steel to components like windows and toilets, and prices did not alleviate once the pandemic ended. Cost increases were further driven by the international tariffs imposed by the Trump Administration, which again disrupted international construction supply chains. Additionally, the national surge in data center construction has increased demand for many construction materials, particularly metals and electrical components.

More recently, the U.S.-Israeli war with Iran, Iran’s closure of the Strait of Hormuz, and the Trump Administration’s declaration to further blockade the Strait, has affected oil prices and shipping costs, driving up the cost of construction. These cost increases have already led to abandoned construction projects across the country and are potentially making construction harder here in NYC.

Soft costs

The term “soft costs” refers to the non-physical aspects of construction such as project planning, design, permitting, procurement and finance. Experts on public capital projects estimate that in NYC soft costs can increase budgets by as much as 21 percent for major endeavors like the Second Avenue Subway. Delays often increase soft costs, and certain features of the NYC public capital project process can cause project setbacks, such as changes of scope by requesting agencies, attaining approval from the Office of Management and Budget (“OMB”) for budget amendments, or follow-up to questions from the Office of the NYC Comptroller (“Comptroller”) during the contract registration process., An assessment of over 1000 DDC projects performed by the Comptroller found an average delay of three and a half years, with inadequate project management to actively mitigate delays or track costs. Perhaps unintuitively, the State requirement for agencies to select the lowest responsible bidder on Requests for Proposals (“RFPs”) can increase costs upon delivery because the lowest responsible bidder may plan and perform poorly due to attempts to keep costs low or general inexperience, leading to months-long delays. Uncooperative utility companies can also contribute to soft costs by failing to advise on the location of underground assets, extending the planning process.

Overall, soft costs and delays have proved difficult to track, for example, the Comptroller’s audit found that DDC does not track cost differentials from initiation to completion in its Benchmark project management tool. Moreover, the agency does not pool detailed spreadsheets of budget statuses or detailed expenditures maintained by individual project managers or budget staff.

The Capital Process Reform Task Force

In April 2022, then-Mayor Eric Adams and then-First Deputy Mayor Lorraine Grillo convened a Capital Process Reform Task Force (“Task Force”) to initiate a comprehensive review of the City’s capital process from initiation to delivery. The Task Force included representatives from engineering and construction firms, building trades unions, and utilities, as well as the Comptroller and nine city agencies and authorities: DDC, DOT, MOCS, OMB, the Department of Parks and Recreation (“Parks”), the Department of Environmental Protection (“DEP”), the Economic Development Corporation, the School Construction Authority (“SCA”), and the Law Department.

In January 2023, the Task Force released its recommendations for policy reform. These recommendations included a mix of nine pieces of state legislation and 30 internal changes, divided into six major categories: Improve the Project Pipeline, Reform Procurement, Streamline Approvals, Grow the Number of New Yorkers who can Participate, Manage Projects More Effectively, and Performance Management and Public Reporting.

The tables below list the Task Force recommendations and their state of implementation.,

State Legislative Reforms

| Recommendation | Status |
| --- | --- |
| Allow the city to require electronic bids | Electronic bidding legislation was signed into law in 2023 and MOCS rolled out a city-wide policy in March 2024. |
| Allow the City’s Procurement Policy Board to update the public hearing threshold and allow for public notice | State legislation allowing for public notice and online comments for contracts over $100,000 passed both houses in 2024 and was signed into law by Governor Hochul in November 2024. (A8864) |
| Increase M/WBE small purchase threshold from $1M to $1.5M | State legislation for M/WBE discretionary spending was signed into law in 2023 and this increased the NYC threshold. |
| Allow M/WBE mentorship programs at all agencies | Executive Order 59 of 2025 created the Centralized Construction Mentorship Program. |
| Allow agencies to use on-step progressive design build | State legislation expanding DDC’s alternative delivery authorization passed both houses in June 2024 and was signed into law by the Governor Hochul in November 2024. |
| Establish DDC as an Authority | This remains on the legislative agenda. |
| Allow agencies to use Construction Manager-Build and Construction Manager-at-Risk | Legislation signed by the Governor in November 2024 allowed CM-Build for libraries and cultural facilities on City-owned land worth over $5 million. CMAR for agencies has not passed the legislature. |
| Create a New York State Insurance Fund pilot program to provide an additional insurance option for M/WBEs and small contractors | Legislation was introduced in both 2024 and 2025 but not passed. |
| Allow the City to Use Owner-Controlled Insurance Programs and Contractor-Controlled Insurance Programs | Legislation was passed and signed into law in 2023. |

Internal Reforms

| Recommendation | Status |
| --- | --- |
| Double the number of projects that use the Capital Project Scope Development Fund | OMB planned to double the number of projects from 10 to 20 by 2025. |
| Host Capital Project Coordination Expos to coordinate with elected officials on projects that may receive discretionary funding | SCA and Parks had convened expos with Council Members by 2024. |
| Create a template and establish standard response times for the Certificate to Proceed process | Certificate to Proceed template was introduced in 2023, while a digital submission tracking system debuted in 2024. |
| Revise Comptroller’s Directive 10 to update interpretations of capital eligibility in limited scenarios when warranted | The Comptroller released a revised Directive 10 in February 2023. |
| Create new Capital Approval Standards to streamline the Certificate to Proceed Process with projects known to be capitally eligible | OMB released new Capital Approval Standards for five work types and plans to reassess in Fiscal Year 2026. |
| Reset existing Capital Approval Standards thresholds and update all Capital Approval Standards every other year based on industry standard construction cost indices | OMB adjusted thresholds for three work types in Fiscal Year 2024, reviewed a fourth in Fiscal Year 2025, and plans to revisit cost thresholds in Fiscal Year 2026, with regular revisions scheduled every two years. |
| Request a five-fold increase to Finance Control Board contract review thresholds based on growth in the City’s budget | New guidelines reflecting the five-fold increase became effective in January 2023. |
| Repeal EO102 of 2007 that includes redundant steps to verify payment of prevailing wages | Executive Order 35 of 2023 repealed Executive Order 102 of 2007. |
| Revise EO50 implementation so compliance with EEO is verified with a single submission by a vendor, rather than multiple submissions for each contract held by the vendor | The Department of Small Business Services completed a rule change and new rules are in effect as of November 2023, allowing verification of a single submission per vendor rather than multiple submissions for separate contracts. |
| Host Project Labor Agreement educational sessions | MOCS developed materials on project labor agreements and held educational sessions in 2025. |
| Create a future projects and procurement document database | This remained under development in 2025. |
| Ensure M/WBE pre-qualified lists are developed at all agencies | By the end of 2025, the Department of Citywide Administrative Services, DDC, DOT, Parks, and DEP all planned to have pre-qualified M/WBE lists. |
| Utilize Early Construction Completion Incentives | DDC, DEP, DOT and Parks have adopted this tool on some projects. |
| Identify an ombudsman at each capital agency so contractors and subcontractors can obtain information or resolve disputes | According to an update on the Capital Process Reform Task Force, all capital agencies had identified ombudspersons by the end of 2024. |
| Utilize price adjustment for Fuel, Steel, Asphalt | DDC, DEP, DOT, and Parks have adopted this tool on certain projects. |
| Institute engineering review to optimize cost effectiveness | DDC, DEP, DOT, and Parks have adopted this tool on certain projects. |
| Coordinate closely with utilities | City Hall started convening a quarterly utility task force and breakout meetings with agencies to handle electrification requests and infrastructure interference coordination. |
| Enhance mobilization payment | DDC, DEP, DOT, and Parks have adopted this tool on certain projects. |
| Expand Expanded Work Allowance for unforeseen field conditions from DDC pilot to all agencies | A pilot was made permanent in June 2025. |
| Create service level agreements governing change orders | Agencies were still developing these in 2025. |
| More efficient processing of certain non-Expanded Work Allowance change orders | OMB launched workflow improvement for these change orders in 2023. |
| Streamline and standardize invoice checklists | Agencies planned to launch these checklists in 2025. |
| Track invoices from date of draft invoice to final approved invoice | This had been adopted by the end of 2024. |
| Pilot tying payment commitment to date of draft invoice | This pilot began in 2024. |
| Pilot program for self-management of small projects | This pilot began in 2025. |
| Shorten timeline for equipment purchases at cultural institutions | Department of Cultural Affairs hired three new program managers and standardized bundling of equipment procurement to accelerate the process. |
| Implement local Law 37 Capital Project Tracker | NYC Capital Projects Dashboard launched in Fall 2023 with planned updates three times annually. |

Project Delivery

Project delivery is one of the most important aspects of a construction project and is the way in which the project is planned, executed, and completed. As many different types of projects exist under the City’s portfolio, DDC primarily uses forms of design-build and Construction Management-Build (“CM-Build”) in project delivery. DDC calls this approach: “Alternative Delivery.” Alternative Delivery leverages collaboration to complete projects faster and more efficiently. This is done by allowing the designer, builder, and the City to work together earlier in the process of project delivery, which ultimately reduces risk and ensures that public facilities open faster.

Public Works Investment Act

Until seven years ago, under state law, DDC, as well as other agencies, were required to use a design-bid-build model. That model required agencies to hire a designer, to complete a design, and to award construction to the lowest qualified bidder. In 2019, the state passed the Public Works Investment Act (“PWIA”), which authorized DDC and other capital agencies in NYC to use what is now known as traditional design-build delivery on certain projects. In 2024, the PWIA was expanded to authorize DDC to use a one-step solicitation process called progressive design-build (“PDB”) on resiliency and infrastructure projects, as well as CM-Build on libraries and cultural institutions on City-owned land. This expanded toolkit allows DDC greater procurement flexibility and the ability to select the best project delivery method based on the specific type of project. The legislation has since been extended through 2029.

The PWIA requires the use of project labor agreements (“PLAs”) for all Alternative Delivery contracts. PLAs establish consistent work rules across construction projects, reduce the administrative burden and costs on construction agencies, and ensure that City residents and businesses are provided the opportunity to work on City projects. In addition, PLAs provide opportunities and flexibility for Minority and Women-Owned Business Enterprises (“M/WBEs”). Notably, DDC’s M/WBE utilization rate for design-build and CM-build projects is two times higher than the rate for low-bid contracts, with set M/WBE participation goals at 30 percent for both the design and construction phases.

Alternative Delivery

Design-Build

According to the Federal Highway Administration, design-build is a project delivery method that combines two usually separate services into a single contract, thereby allowing owners to administer a single fixed-fee contract for planning services and construction. Traditionally, other project delivery methods separate contracts for design and construction; however, design-build’s utilization of a single contract looks to streamline the process and allow for more efficient project delivery.

According to the Design Build Institute of America, a nonprofit professional association that advocates for design-build, design-build is one of the fastest growing and most commonly used project delivery methods in the United States and has become widely utilized in both private and public sector projects, including building construction, transportation and water/wastewater markets. According to DDC, design-build allows the agency “to complete public projects faster and more efficiently” through collaboration, efficiency, and risk reduction. Moreover, it allows DDC to prioritize design, qualifications, and experience, with an emphasis on best value, when selecting project vendors. However, despite its advantages, DDC also notes in the Design-Build Program 2024 Progress Report to the New York State Legislature (“2024 Progress Report”) that design-build “is far from the only tool in the procurement toolbox” and that it is best suited for “new buildings, where the project requirements and site conditions are well-defined upfront, and less suitable for complex infrastructure projects or building renovations, where site conditions heavily influence design and delivery.”

In February 2025, the Mayor’s Office and DDC announced that the City, through utilizing design-build on 42 of its then-current capital projects, anticipated saving a combined total of 50 years of project time and $1.4 billion. In addition to these projects, at the time, the City had 46 design-build projects in the planning and procurement phases across several agencies.  At the time, former DDC Commissioner Tom Foley noted that design-build was “speeding up projects, reducing delays, saving money and delivering important capital projects faster than we’ve ever been able to before outside of emergency situations.”

Alternative Delivery Two-Step Procurement Process to Select Vendors

Currently, DDC uses a two-step procurement system during its Alternative Delivery vendor selection process. During this process, a Request for Qualifications (“RFQ”) is published to compile a list of qualified vendors (also known as proposers). Next, proposers provide a Statement of Qualifications (“SOQ”) outlining their capacity to successfully finish the design and construction work for the planned project. DDC then reviews and ranks SOQs and generates a short-list of the most qualified proposers eligible to participate in the RFP phase. During this phase, DDC releases scoping documents, including detailed information on project requirements, and a draft of the agreement. Firms that were not eligible for the RFQ list from the first part of the process are given the opportunity to partner with the teams on DDC’s list. During the in-market phase, DDC may conduct “Collaborative Dialogue Meetings” with the proposers to advance shared understanding of the project’s schedule and budget in an effort to reduce risk.

(The above image shows DDC’s Two-Step Procurement Process)

Design-Build Program 2024 Progress Report

Between 2021 and 2024, DDC released an annual report titled The City of New York Design-Build Program Progress Report to the New York State Legislature (“Progress Report”), which provided an overview of the agency’s use of design-build project delivery. According to the most recent report released in 2024, in Fiscal Year 2024, DDC registered four design-build contracts, representing all of the City’s design-build contracts as of that report’s release, totaling $57 million. As of the release of the report, DDC was utilizing design-build in constructing new buildings for the Shirley Chisholm Recreation Center in Brooklyn and Mary Cali Dalton Recreation Center in Staten Island. Overall, through employing design-build in these projects, DDC anticipated completing construction at least two years sooner than if they had utilized the more traditional design-bid-build low-bid methods. In addition, DDC was applying design-build for Parks’ maintenance facilities at Orchard Beach in the Bronx and in Arverne, Queens.

Notably, DDC is making use of design-build for one of its largest projects: the Borough-Based Jails Program. As part of the City’s plan to close the jail on Rikers Island, DDC will be employing design-build to construct smaller jails in Manhattan, Brooklyn, Queens, and the Bronx. DDC is awarding separate design-build contracts for each of the four facilities and for early work packages at each site, resulting in a total of nine contracts. According to DDC’s 2024 Progress Report, the agency has completed a garage and community space in Kew Gardens, Queens as part of the Borough-Based Jails Program. DDC noted that, with design-build, they completed the project three years faster than typical project delivery methods and exceeded their 30 percent M/WBE participation goals for design and construction. In addition, all four Borough-Based Jail dismantle and site preparation projects were completed within budget and on schedule. According to DDC, this was accomplished twice as fast as if the agency utilized traditional design-bid-build projects and exceeded the agency’s 30 percent M/WBE participation goal. Moreover, DDC anticipates comparable results when they begin constructing the new jail facilities.

According to the 2024 Progress Report, DDC was managing 22 projects within its design-build portfolio, with an estimated cost greater than $14 billion. These included: $190.5 million in funding for four infrastructure projects, $670 million for nine public buildings projects, and $13.4 billion for nine projects relating to the Borough-Based Jails Program. Overall, these projects include or included support facilities for Parks, raised crosswalks for the DOT, deep sewer manholes for the DEP, and the construction of new jails for the NYC Department of Correction.

The report noted that there were currently four projects in DOT’s design-build portfolio, totaling $400 million. DOT’s Division of Bridges will utilize design-build for three projects, totaling $355 million, and its Ferry Division will employ the method for one project, totaling $45 million. DOT is working with the NYS Department of Transportation to ensure policies and procedures adhere to federal guidelines around bridges and ferries due to the possible influx of federal funding into these projects. The projects are the following:

- East 183rd Street Bridge and East 188th Street Bridge over Metro North Railroad Harlem Line;

- Belt Short Parkway over Sheepshead Bay Road/Ocean Avenue/Bedford Avenue/Nostrand Avenue;

- 191st Street Pedestrian Tunnel over Broadway and IRT #1 Subway; and

- Ferry Terminal Floodproofing.

According to the 2024 Progress Report, DOT’s implementation of design-build is expected to help the agency reduce project durations and costs, largely through: avoiding change orders without the collaboration of the contractor, reducing administrative burden on project development and completion, improving coordination and innovation, and implementing more efficient construction schedules due to the contractor and designer working together.

2025: A Blueprint for Design-Build

Prior to the end of the Adams administration, DDC released a report titled: 2025: A Blueprint for Design-Build. As of August 2025, DDC awarded 12 contracts valued at over $800 million in its Public Buildings and Infrastructure Portfolio, which the agency believes will save years in construction time while maintaining high quality standards and fostering collaboration previously impossible under the old design-bid-build model. As of the report’s publishing, DDC had completed all five early works projects in the Borough-Based Jails program and had completed its first two projects in the design-build pilot program.

In 2025, DDC expanded its alternative delivery program to include additional major projects. These projects include the East Side Greenway 14th Street Connector in Manhattan and Westchester Square Library in the Bronx. DDC is working towards expanding the State authorization for it alternative delivery program to be able to provide for a full alternative delivery toolkit. In 2026, DDC is slated to complete six design-build projects, as part of the initial pilot program.

The report outlines several strategies that DDC is utilizing to ensure that it is realizing the full potential of alternative delivery, including:

- Building Expertise and Changing the Culture: DDC has begun training its team and partners in design-build delivery. As of mid-2025, DDC trained over 150 of its own staff across several divisions, while also streamlining contracting and procurement processes;

- Building the Industry: DDC has expanded its programs by setting commercially friendly terms and communicating what is different about design-build, thereby welcoming new partners to the table. As a result of this, DDC has received an average of 11.6 Statement of Qualifications submissions for every design-build procurement in its pilot portfolio;

- Continuous Learning: DDC launched its initial design-build projects as a pilot with the intent to learn and adapt the program as it develops. DDC continues to engage regularly with industry associations and other owners to share challenges, best practices and lessons learned;

- Planning: DDC assesses every project to determine the appropriate delivery method and has expanded its planning process by having scoping workshops and conducting detailed site investigations;

- Solicitation: DDC utilizes scoping documents with performance specifications rather than prescriptive requirements or bridging documents to allow flexibility within the project. DDC works to ensure the right level of effort during the in-market stage is provided, and follows specific best practices like shortlisting three design-build teams and providing stipends to unsuccessful but responsive proposers;

- Contract Terms: DDC has developed all-new contract terms to take full advantage of Alternative Delivery’s potential;

- Post-Award Practices: After award and site validation, DDC looks to ensure that design-builders are set up for success by streamlining City regulatory approvals, coordinating design feedback and encouraging strong partnerships. DDC also organizes Principals Meetings to address challenges and ensure that the organizations remain aligned in their leadership; and

- M/WBE Participation: Alternative Delivery tools dramatically expand the City’s ability to engage M/WBEs and local workforce, with clear results: DDC’s M/WBE participation rate for design-build and CM-build projects is over 10 percent higher than the rate for design-bid-build. DDC also sets mandatory 30 percent M/WBE participation goals.

CM-Build

Unlike design-build, where a single entity holds responsibility for both design and construction under one contract, CM-Build is a distinct delivery method under which the City retains a separate design contract, and hires a construction management firm to hold the underlying construction contracts and manage the overall project. CM-Build procurements follow the same two-step RFP process used for design-build, with a shortlist of up to three firms invited to respond to the RFP.

While the City's architect retains design authority, the construction manager is onboarded early in the design phase, which allows the CM firm and the designer to collaborate before the project scope is fully finalized. This early integration enables problems to be identified and resolved during design rather than in the field, which reduces the risk of costly change orders and schedule disruptions that often occur in the traditional design-bid-build model.

DDC first deployed CM-Build under emergency authority during the COVID pandemic. With standard procurement rules suspended, DDC used CM-Build to construct a 470-bed field hospital in 11 days, three COVID centers in seven months, and several testing and vaccination sites across the City in an average of seven days each. DDC also used CM-Build to build temporary asylum facilities during the migrant crisis. These demonstrated the capacity of CM-Build to reduce project timelines when accelerated procurement options were available.

In November 2024, Governor Hochul signed legislation authorizing DDC to use CM-Build outside of emergency conditions, specifically for projects at libraries and cultural institutions on City-owned land. DDC has estimated that the method can save at least one year on a standard project and up to two full years on larger projects compared to traditional procurement methods like competitive sealed bidding.

In March 2026, DDC announced the launch of its first formal CM-Build pilot program for five city projects: the $160 million rebuild of 70 Mulberry Street in Chinatown, renovations of the Spring Creek Library, the Harlem Stage Gatehouse, Snug Harbor and the Staten Island Museum, and Woodside Library.

LEGISLATIVE ANALYSIS

Int. No. 263: A Local Law in relation to developing a strategic blueprint to reduce capital project durations by at least 25 percent

This bill would require DDC, in coordination with other agencies, to create a strategic blueprint for reducing the average capital project duration by at least 25 percent. The blueprint would be required to address incentives for early project completion, coordination between agencies and utility companies, and standardization of capital project processes, timelines and forms. DDC would be required to file the blueprint with the Mayor and the Council and post the blueprint on its website. The bill would take effect immediately.

Int. No. 465: A Local Law in relation to a study and report on the expansion of ferry service along the Harlem River

This bill would require DOT to coordinate with the City’s Economic Development Corporation, which is contracted to operate NYC Ferry, to study the feasibility of extending NYC Ferry access to the West Bronx along the Harlem River. The bill would take effect immediately and give DOT one year to submit a report based on the study’s findings to the Speaker and Mayor and to publish that report on its website.

Res. No. 264: Resolution calling on the New York State Legislature to introduce and pass, and the New York State Governor to sign, legislation to grant permanent and expanded Design-Build authority to all New York City agencies

This resolution would call on the New York State Legislature to introduce and pass, and the New York State Governor to sign, legislation to grant permanent and expanded Design-Build authority to all NYC agencies. Currently, only a limited number of City agencies—including DDC, DOT, DEP, Parks, Health and Hospitals Corporation, SCA, and NYC Housing Authority—are authorized to use Design-Build in their projects.

Int. No. 263

By Councils Member Krishnan, Louis, Brooks-Powers, Abreu, Brewer, Hudson, Hanif, Stevens, Ung, Feliz, Schulman and Morano

..Title

A Local Law in relation to developing a strategic blueprint to reduce capital project durations by at least 25 percent

..Body

Be it enacted by the Council as follows:

Section 1. By no later than December 1, 2023, the department of design and construction shall, in coordination with other agencies as appropriate, prepare and file with the mayor and the council, and post on its website, a strategic blueprint to reduce the average duration of capital projects by at least 25 percent. Such blueprint shall review, at a minimum, early completion incentives; standardization of processes, timelines, and forms; and agency coordination with utility companies.

§ 2. This local law takes effect immediately.

MJT

LSR #11638

Int. #0046-2024

1/6/2026 12:10 PM

Int. No. 465

By Council Members Stevens, De La Rosa, Farías, Brooks-Powers, Williams, Louis, J. Sanchez, Schulman, Riley, Dinowitz and P. Sanchez

..Title

A Local Law in relation to a study and report on the expansion of ferry service along the Harlem River

..Body

Be it enacted by the Council as follows:

Section 1. a. Definitions. For purposes of this local law, the following terms have the following meanings:

City. The term "city" means the city of New York.

Commissioner. The term "commissioner" means the commissioner of transportation.

Contracted Entity. The term “contracted entity” has the same meaning as such term is defined in section 22-821 of the administrative code of the city of New York.

Department. The term "department" means the department of transportation.

Harlem River. The term "Harlem River" means the tidal strait in the city that separates the borough of Manhattan from the borough of the Bronx.

West Bronx. The term "West Bronx" means the area of the borough of the Bronx located west of the Bronx River and adjacent to the Harlem River.

b. The commissioner, in coordination with the contracted entity, shall conduct a study on the feasibility of expanding ferry service access along the Harlem River, with a particular focus on service to the West Bronx. Through such study, the commissioner shall:

1. Identify potential locations for the siting of new ferry terminals along the Harlem River, with a focus on identifying such locations in the West Bronx;

2. Identify local benefits that would result from such siting, including but not limited to improved transit access, reduced travel times, and enhanced connectivity to employment centers and other destinations for West Bronx residents and other communities along the Harlem River;

3. Identify logistical challenges involved with such siting, including but not limited to:

(i) the size and structure of ferry boats;

(ii) the depth and navigability of the Harlem River;

(iii) the availability and utility of existing piers and waterfront facilities;

(iv) potential conflicts with existing maritime uses;

(v) any necessary coordination with state or federal agencies having jurisdiction over the Harlem River;

4. Propose solutions, if any, to such challenges; and

5. Estimate the projected costs associated with such siting and implementation of such solutions.

c. No later than one year after the effective date of this local law, the commissioner shall submit to the mayor and speaker of the council, and post on the department's website, a report on the findings of the study required under subdivision b of this section.

§ 2. This local law takes effect immediately.

ARP

LS #17714

Int. #1492-2025

1/8/2026 2:41 PM

Res. No. 264

..Title

Resolution calling on the New York State Legislature to introduce and pass, and the New York State Governor to sign, legislation to grant permanent and expanded Design-Build authority to all New York City agencies

..Body

By Council Members Lee, Louis, Feliz and Schulman

Whereas, Every year, New York City (NYC) manages billions of dollars in capital construction projects related to things such as infrastructure, schools, parks, and housing; and

Whereas, To complete these projects, NYC utilizes a range of project delivery methods, one of which is the use of Design-Build; and

Whereas, Design-Build is a project delivery method that combines two, usually separate services into a single contract to allow owners to execute a single, fixed-fee contract for both architectural and engineering services as well as construction; and

Whereas, Under this method, the design-builder assumes responsibility for the majority of the design work and all construction activities, along with the risks that come with providing these services; and

Whereas, The NYC Department of Transportation (DOT) states that Design-Build is a way to streamline decision-making, facilitate more transparent partnerships with designers, contractors, and other stakeholders, improve the quality of project delivery, and create pathways to increased innovation and sustainable solutions; and

Whereas, In February of 2025, the City announced that it was saving 50 years of project time and $1.4 billion on 42 current capital projects that are utilizing Design-Build, with projects on track to be completed faster and with an anticipated 10 percent cost savings compared to projects using the traditional lowest-bidder system; and

Whereas, To build on this success, the City is expanding the use of Design-Build for 46 additional projects that are in planning and procurement across several NYC agencies; and

Whereas, Despite the positives that have been seen using Design-Build for project delivery, under New York State (NYS) law, a limited number of NYC agencies, including the Department of Design and Construction, Department of Environmental Protection, DOT, Department of Parks and Recreation, Health and Hospitals Corporation, School Construction Authority, and NYC Housing Authority, are allowed to use Design-Build in their projects; and

Whereas, As a result, NYC agencies without the authority to use Design-Build in their projects may continue to face delays, cost overruns, and procurement challenges under outdated delivery models; and

Whereas, To ensure projects are performed more efficiently to meet current infrastructure, climate, and housing needs in NYC, NYS should implement legislation that would allow all NYC agencies to utilize Design-Build in their projects; now, therefore, be it

Resolved, That the Council of the City of New York calls upon the New York State Legislature to introduce and pass, and the New York State Governor to sign, legislation to grant permanent and expanded Design-Build authority to all New York City agencies.

KK

LS #19329

Res. #0886-2025

1/5/2026 4:27 PM

About NYC DDC, N.Y.C. Dep’t of Design & Constr., https://www.nyc.gov/site/ddc/about/about-ddc.page (last visited Apr. 21, 2026).

Id.

Id.

About MOCS, Mayor’s Office of Contract Servs., https://www.nyc.gov/site/mocs/about/about-mocs.page (last visited Apr. 21, 2026).

N.Y.C. Charter §§ 20-t(c)(6), (7)

Id. at §§ 20-t(c)(1), (5).

Id. at § 20-t(c)(8).

About PASSPort, Mayor’s Office of Contract Servs., https://www.nyc.gov/site/mocs/passport/about-passport.page (last visited Apr. 21, 2026).

About NYC DOT, N.Y.C. Dep’t of Transp., https://www1.nyc.gov/html/dot/html/about/about.shtml (last visited Apr. 21, 2026).

Id.

Id.

Id.

Id.

About Cultural Affairs, N.Y.C. Dep’t of Cultural Affairs, https://www.nyc.gov/site/dcla/about/about-cultural-affairs.page (last visited Apr. 21, 2026).

Id.

Id.; A Unique Partnership, Cultural Insts. Grp. NYC, https://www.cignyc.org/about (last visited Apr. 21, 2026).

About CDF / Registration, N.Y.C. Dep’t of Cultural Affairs, https://www.nyc.gov/site/dcla/cultural-funding/about-cdf-registration.page (last visited Apr. 21, 2026).

Capital Funding, N.Y.C. Dep’t of Cultural Affairs, https://www.nyc.gov/site/dcla/cultural-funding/capital-funding.page (last visited Apr. 21, 2026).

About Cultural Affairs, N.Y.C. Dep’t of Cultural Affairs, https://www.nyc.gov/site/dcla/about/about-cultural-affairs.page (last visited Apr. 21, 2026).

New York City Council, Report on the Fiscal 2027 Preliminary Plan, the Fiscal 2027 Preliminary Capital Commitment Plan, and the Fiscal 2026 Preliminary Mayor’s Management Report for the Committee on Cultural Affairs, Libraries and International Relations 1, available at https://legistar.council.nyc.gov/LegislationDetail.aspx?ID=7929518&GUID=232A8052-7F4C-47D7-8EF0-8729226‌B9378‌&Options=&Search=.

Press Release, Turner & Townsend, US cities most expensive places to build globally (July 8, 2025), https://www.turnerandtownsend.com/news/us-cities-most-expensive-places-to-build-globally/.

Id.

Sean Campion, Why it Costs So Much to Build in New York City, Vital City (Sep. 17, 2025), https://www.vital‌citynyc‌.org/‌why-it-costs-so-much-to-build-in-new-york-city/.

Tiffany Emmett, Global construction cost performance, Turner & Townsend, https://publications‌.turnerandtownsend.com/‌global-construction-market-intelligence-2025/global-construction-cost-trends#block-a3072‌4da‌-c24c-4281-8d03-7b72b8e1252e (last visited Apr. 21, 2026).

Id.

See National Crane Certification Requirement for NYC HMO Licenses, N.Y.C. Dep’t of Bldgs., https://www.nyc.gov/site/buildings/industry/hoisting-nccco-cic-requirements.page (last visited Apr. 21, 2026); see also New York City Central, Nat’l Comm’n for the Certification of Crane Operators, https://www.nccco.org/‌nccco/resources/industry-resources/state-licensing/new-york-city-central (last visited Apr. 21, 2026).

See generally Michael R. Hattery, PhD, The Cost of Labor Law 240 on New York’s Economy and Public Infrastructure (Dec. 13, 2013), Nelson A. Rockefeller Inst. of Gov’t, State Univ. N.Y. Albany, https://verticalaccessllc.wordpress.com/wp-content/uploads/2014/03/2014-02-study-the-costs-of-labor-law-240-on-new-york-economy-and-public-infrastructure.pdf?ref=vitalcitynyc.org.

Paul Brumlik, Construction Worker Prevailing Wage Schedule, at 1, Office of the N.Y.C. Comptroller (Jan. 19, 2026), https://comptroller.nyc.gov/wp-content/uploads/documents/ConstructionWorkersSchedule-2025-2026.pdf.

See Russell Weaver & Anne Marie Brady, Buffalo Co-Lab & Worker Inst., Cornell Univ., Building Responsible Projects in New York City: Assessing the Impact of Prevailing Wage Benefits on Workers, Contractors, and the New York City Economy 6 (Sep. 12, 2023), https://ecommons.cornell.edu/‌server/api/core/bitstreams/2615d93d-fc5e-4b1f-90c0-c28702110688/content.

E.J. McMahon and Kent Gardner, Empire Ctr. For Pub. Pol’y, Prevailing Waste: New York’s Costly Public Works Pay Mandate 15 (2017), https://www.empirecenter.org/wp-content/uploads/2017/04/PW-final.pdf.

See Russell Ormiston, Dale Berman, & Matt Hinkel, Econ. Pol’y Inst., New York’s prevailing wage law: A cost-benefit analysis (Feb. 14, 2018), https://www.epi.org/publication/new-yorks-prevailing-wage-law-a-cost-benefit-analysis/.

N.Y.C. Indep. Budget Office , The Impact of Prevailing Wage Requirements on Affordable Housing Construction in New York City 1 (Feb. 2016), https://www.ibo.nyc.ny.us/iboreports/the-impact-of-prevailing-wage-requirement-on-affordable-housing-construction-in-new-york-city.pdf.

Jeffrey Passel and Jens Manuel Krogstad, Pew Research Ctr. U.S. Unauthorized Immigrant Population Reached a Record 14 Million in 2023 17 (Aug. 21, 2025), https://www.pewresearch.org/wp-content/uploads/sites/20/2025/08/RE_2025.08.21_Unauthorized-Immigrants_REPORT.pdf.

Sydney Ember, Builders Find Hardship in Trump’s Tariffs and Deportations, N.Y. Times (Nov. 2, 2025), https://www.nytimes.com/2025/11/02/business/construction-tariffs-immigration-trump.html.

Sebastian Obando, 5 years after COVID hit, contractors still wait for prices to come down, Constr. Dive (Mar. 11, 2025), https://www.constructiondive.com/news/covid-impact-construction-prices-materials/742087/.

Sebastian Obando, Tariffs drove construction input prices up to start 2026, Constr. Dive (Feb. 27, 2026), https://www.constructiondive.com/news/tariffs-construction-input-prices-january-2026/813419/.

Sebastian Obando, After years of stability, construction materials costs are heating up again, Constr. Dive (Jan. 23, 2026), https://www.constructiondive.com/news/construction-materials-costs-increase-gordian/810419/.

See Will Parker, Construction Business Taking a Hit From Iran Conflict, Wall St. J. (Apr. 10, 2026), https://www.wsj.com/economy/construction-business-taking-a-hit-from-iran-conflict-914cbca4.

See Sebastian Obando, Iran war impacts on oil prices spiked construction stress, increased abandonments, Constr. Dive (Apr. 14, 2026), https://www.constructiondive.com/news/iran-war-oil-price-construction-stress/817413/.

Jimmy Primsky & Taylor Riso, Soft Costs and How They Impact Construction Outcome, Procore (July 22, 2025), https://www.procore.com/library/construction-soft-costs.

Eric Goldwyn, Alon Levy, Elif Ensari, & Marco Chitti, Marron Inst. of Urban Mgmt., N.Y.U., Transit Costs Project: Executive Summary 13, 21 (2017), https://transitcosts.com/wp-content/uploads/‌TCP_Executive‌_Summary.pdf.

See generally Maura Hayes-Chaffe, Office of the N.Y.C. Comptroller, Audit Report of the Department of Design and Construction’s Mitigation of Delays and Cost Overruns on Capital Construction Projects (Dec. 26, 2025), https://comptroller.nyc.gov/wp-content/uploads/2026/02/SE23-073A.pdf.

See John Surico, Ctr. for an Urban Future, Stretching New York City’s Capital Dollars: A Blueprint for Fixing NYC’s Broken Capital Construction Process for Social Infrastructure 11–17 (April 2021), https://nycfuture.org/pdf/CUF_Stretching_Capital_Dollars_4-21.pdf.

Hayes-Chaffe, supra note 42 at 13–15.

Surico, supra note 43 at 13.

Hayes-Chaffe, supra note 42 at 10–11.

Id. at 11.

N.Y.C. Capital Process Reform Task Force, Initial Recommendations 1 (Oct. 2022), https://www.nyc.gov/‌assets/‌mocs/downloads/Regulations/legislative-regulatory-reform/CP-Reform-Task-Force.pdf.

Id.

N.Y.C. Capital Process Reform Task Force, 2022 Year-end Report 10 (Jan. 2023), https://www.nyc.gov/‌content/dam/nycgov/mayors-office/downloads/pdf/press-releases/2023/CP_ReformTaskForce.pdf.

See generally N.Y.C. Capital Process Reform Task Force, Build Better NYC: 2024 Year-end report (Jan. 2025), https://www.nyc.gov/assets/home/downloads/pdf/press-releases/2024/‌Capital%20Process%20Reform%20‌Report.pdf.

See generally N.Y.C. Dep’t of Design and Constr., 2025 Strategic Blueprint (Aug. 2025), https://www.nyc.gov/assets/ddc/downloads/publications/2025_Strategic_Blueprint.pdf.

Alternative Delivery, N.Y.C. Dep’t of Design and Constr., https://www.nyc.gov/site/ddc/contracts/alternative-delivery.page (last visited Apr. 21, 2026).

Id.

N.Y.C. Dep’t of Design & Constr., 2025: A Blueprint for Design-Build 3 (2025), https://www.nyc.gov/assets/ddc/downloads/contracts/2025_A_Blueprint_for_Design_Build.pdf [hereinafter 2025 Blueprint].

Id.

Alternative Delivery, N.Y.C. Dep’t of Design and Constr., https://www.nyc.gov/site/ddc/contracts/alternative-delivery.page (last visited Apr. 21, 2026).

Id.

Id.

Id.

Id.

Id.

Id.

Id.

Design Build, Fed. Highway Admin., https://www.fhwa.dot.gov/‌ipd/alternative_project_delivery/‌defined/‌new_build_facilities/‌design_build.aspx (last visited Apr. 21, 2026).

What is Design-Build?, Design-Build Inst. of Am., https://dbia.org/what-is-design-build/ (last visited Apr. 21, 2026).

Id.

Alternative Delivery, N.Y.C. Dep’t of Design and Constr., https://www.nyc.gov/site/ddc/contracts/alternative-delivery.page (last visited Apr. 21, 2026).

Id.

N.Y.C. Dep’t of Design & Constr., Design-Build Program 2024 Progress Report to the New York State Legislature 3 (2024),: https://www.nyc.gov/assets/ddc/downloads/contracts/2024_Design_Build_Report.pdf [hereinafter 2024 Progress Report].

Press Release, N.Y.C. Dep’t of Design & Constr., Design-Build Saving Over 50 Years and $1.4 Billion On Just 42 City Projects (Feb. 20, 2025), https://www.nyc.gov/site/ddc/about/press-releases/2025/pr-022025-DesignBuild.page.

Id.

Id.

Alternative Delivery, N.Y.C. Dep’t of Design and Constr., https://www.nyc.gov/site/ddc/contracts/alternative-delivery.page (last visited Apr. 21, 2026).

Id.

Id.

Id.

Id.

Id.

Id.

Id.

Design-Build at DDC, N.Y.C. Dep’t of Design & Constr., https://www.nyc.gov/‌site/‌ddc/‌contracts/‌designbuild.page (last visited Apr. 21, 2026).

2024 Progress Report, supra note 75 at 4.

Id. at 6.

Id.

Id.

NYC Borough-Based Facilities, City of N.Y., https://rikers.cityofnewyork.us/nyc-borough-based-jails/ (last visited Apr. 21, 2026).

Id.

Id.

2024 Progress Report, supra note 75 at 6.

Id.

Id.

Id.

Id.

Id. at 9.

Id. at 9–10. The Borough-Based Jails Program publicly stated that it was a $15 billion total cost, however, this includes associated expenses that do not fall under DDC’s Design-Build Program.

Id. at 10–16.

Id. at 48.

Id.

Id.

Id.

Id.

Id.

Id.

Id.

See generally 2025 Blueprint, supra note 55.

Id. at 4.

Id.

Id.

Id.

Id.

Id. at 7.

Id. at 8.

Id.

Id.

Id. at 9.

Id.

Id.

Id. at 10.

Id.

See Alternative Delivery, N.Y.C. Dep’t of Design and Constr., https://www.nyc.gov/site/ddc/contracts/alternative-delivery.page (last visited Apr. 21, 2026).

See Press Release, N.Y.C. Dep’t of Design & Constr., Building on Success of Shirley Chisholm Recreation Center, DDC Continues to Grow Its Alternate Delivery Program as the City's First CM-Build Pilot Program Gains Five Projects (Mar. 25, 2026), https://www.nyc.gov/site/ddc/about/press-releases/2026/pr-032526-CMBuild.page.

See id.

See, e.g. Press Release, N.Y.C. Dep’t of Design & Constr., Three Companies Selected to Compete for Contract to Manage Project at 70 Mulberry in Chinatown (July 29, 2025), https://www.nyc.gov/site/ddc/about/press-releases/2025/pr-072925-70Mulberry.page.

See Press Release, N.Y.C. Dep’t of Design & Constr., City Capital Construction Moved Much Faster With Some Restrictions Removed During the Pandemic, Report Finds (Mar. 30, 2021), https://www.nyc.gov/site/ddc/about/press-releases/2021/pr-033021-Report.page.

N.Y.C. Dep’t of Design & Constr., DDC 2020: Delivering Innovation In A Challenging Year 7 (2021), https://www.nyc.gov/assets/ddc/images/content/pages/press-releases/2021/DDC__2020.pdf.

Id. at 13, 22 (noting that each of the three centers were finished roughly four, seven, and six months after initial construction began).

Id. at 21.

See Press Release, N.Y.C. Dep’t of Design & Constr., Building on Success of Shirley Chisholm Recreation Center, DDC Continues to Grow Its Alternate Delivery Program as the City's First CM-Build Pilot Program Gains Five Projects (Mar. 25, 2026), https://www.nyc.gov/site/ddc/about/press-releases/2026/pr-032526-CMBuild.page.

See id.

See id.

See id.